# FYP2 Development Phase & Final Report Map — Week 7 Deadline

状态：planned；待 Codex / Claude Code Repository Audit 后按真实证据更新。 本文将「完整系统先行」解释为：先完成带 transparent mock 的全部系统契约，再在 W3 接入真实 FYP1 baseline 模型；并非 W7 才开始 AI integration。

# A. 依赖驱动的开发阶段

| Week | Priority | Development Goal | Verifiable Exit Criterion | Report Evidence |
| --- | --- | --- | --- | --- |
| W1 | P0 | Repo audit; data/model artifact inventory; API/probability schema freeze; safe tests | 审计完成，真实 model checkpoint 至少可独立运行；知道 current mock 路径与 critical blockers | Updated Ch4 design vs code，Ch5.1–5.2 |
| W2 | P0 | Full system skeleton: React ↔ FastAPI ↔ mock adapters ↔ fusion ↔ database ↔ export; error/loading UI | 完整 replay/CRUD/demo 可运行；mock 显示明显状态，不伪装 trained inference | Ch5.4–5.6 |
| W3 | P0 | Deploy FYP1 MobileNetV3 + XGBoost baseline adapters, real per-input inference | 实际 image+8-feature record → model outputs → RiskScore → API → Dashboard → persisted session；有 smoke log | Ch5.3–5.5 |
| W4 | P1 | ResNet18, RF, LR comparator training + reproducible pipelines; launch bounded tuning | 五模型 train/val/test 固定、至少 baseline comparison 有实际结果，调参计划有日志 | Ch5.3 and Ch6.2 evidence |
| W5 | P1 | Tune MobileNetV3/ResNet18/XGBoost/RF/LR on validation; freeze final models; deploy updated primary checkpoints | 记录搜索空间/次数、seed、best-validation checkpoint、模型比较；test set 未用于选择 | Ch5.3, Ch6.2 |
| W6 | P0/P1 | Build/run E1–E5 minimum scripts; unit/integration/system+negative tests; p50/p95 logging | D0–D3/6x3/fusion/fault test 有真实可重现记录或明确 BLOCKED；CI tests 与故障记录 | Ch6 evaluation assets |
| W7 | P0 | Feature freeze, complete demo, regression/error handling, packaging | 原型使用真实模型推理，关键功能稳定、可追溯、可演示；没有未解决 P0 | Ch5 implementation finalized + Ch6 evidence manifest |

P0 must not wait: source-of-truth risk_update, valid schema, threshold boundaries, freshness handling, both missing, inference adapter failure, session log integrity. 真实 DMD 外部数据申请与图像抽帧可并行但不能占用 Week 7 Critical Path。禁止为了追求更高精度而无限延长 HPO。

# B. 模型训练与调参拆解

| Branch | Main Model | Comparator(s) | Tunable Controls (examples, NOT executed configs) | Model Selection |
| --- | --- | --- | --- | --- |
| Vision | MobileNetV3-Large | ResNet18 | LR, weight decay, freeze/unfreeze, augmentation, early stopping | driver-disjoint validation macro-F1 + inference latency |
| Telemetry | XGBoost | RF, LR | XGB depth/trees/lr; RF depth/trees/leaf; LR C/solver with train-only scaler | validation macro-F1 + per-class recall + latency |

所有实验明确 run_id, train/val/test hashes, config JSON/YAML, seed, git commit, metric artifact, checkpoint。模型比较的 test 必须最后一次执行；外部 DMD 无法下载或 label mapping 不合法时，报告 NOT AVAILABLE，不要改成 synthetic 并称 cross-dataset。

# C. Rubric 对应的 Final Report

## Chapter 4: System Analysis and Design (8 marks; update, not rewrite)

4.1 Functional & Nonfunctional Requirements (include test IDs + traceability).

4.2 AI Branch & Fusion Design (Vision, Telemetry, freshness-weighted fusion, severity mapping, EMA/FSM).

4.3 High-Level System Design (Frontend/Backend/AI modules, single canonical risk_update).

4.4 UML/Behavioral Design (Use Case, Sequence, Data Flow).

4.5 Interface Design (five screens; accessibility/interaction decisions).

Evidence: updated architecture diagrams match actual shipped source, requirements mapped to tests. No implementation metrics here.

## Chapter 5: System Development (8 marks; substantial rewrite)

5.1 Development Environment & Tech Stack.

5.2 Vision/Telemetry Data Preparation & Reproducibility.

5.3 Model Development & Bounded Hyperparameter Tuning (MobileNetV3/ResNet18, XGBoost/RF/LR; configs, final selection, model export; avoid exhaustive results tables here).

5.4 Actual Inference + Fusion + Freshness + Risk-Level + EMA/FSM Implementation.

5.5 FastAPI/React Integration + error/loading/retry UX.

5.6 Session persistence, export, runtime traceability.

Evidence: runtime sequence, model load paths, API contracts, error UI, source code snippets where helpful, environment/version info.

## Chapter 6: Results and Discussion (8 marks for system evaluation; include ML evaluation)

6.1 Evaluation Setup and Data Provenance.

6.2 Model Comparison and Tuning Results (primary vs comparators; final checkpoint selection; external DMD if valid).

6.3 E1 Modality-Specific Robustness (Vision 6×3, Telemetry D0–D3).

6.4 E2 Fusion Effectiveness (clean scenario pairs, five weight settings, no fake severity ground truth).

6.5 E3 Fusion Robustness (missing/stale/normalization, ΔRisk distribution).

6.6 E4 Runtime Robustness (EMA, FSM, inference/API/DB failure and recovery).

6.7 E5 Cross-Layer Robustness (vision corrupt+clean telemetry; reverse; risk attenuation counterexamples).

6.8 Unit/Integration/System/Performance Tests & Error Handling.

6.9 User Acceptance Testing (actual participants/task evidence, not a fabricated study).

6.10 Overall Discussion: what each objective supports, what cannot be claimed, trade-offs.

Evidence: actual executed tables/charts, raw artifacts, reproducibility, test case IDs, failures and limitations. Do not fake performance results.

## Chapter 7: Strengths, Limitations and Future Works (3 marks conclusion)

7.1 Objective Fulfillment Table (Obj 1 fusion framework, Obj 2 severity-aware operational score, Obj 3 repeated inferencing and reliability).

7.2 Strengths (only empirically observed).

7.3 Limitations (unpaired modality datasets, synthetic telemetry, non-calibrated probabilities if still true, no real vehicle-grade safety claim, possible synthetic pairing).

7.4 Future Works (real synchronized paired samples, external validation, reliability-aware/adaptive fusion, edge deployment, calibration if not performed).

Note: Keep Ch1–3 mostly intact, update evaluation methodology when the actual experiment design changes; Abstract <=300 words; APA references.

# D. Rubric-driven evidence priorities

8/30 marks Ch4: requirements completeness + full diagrams + UI design.

8/30 marks Ch5: actual technical modules, UX quality, integration, complexity.

8/30 marks Ch6 system evaluation: unit/integration/system tests, real UAT, robust error handling; model-level AI figures do not replace these software tests.

3/30 conclusion: state which objectives were fulfilled, with test/evaluation IDs.

2 abstract + 1 references: <=300-word abstract, APA and currency.

Important distinctions for examiner/Viva: D0 already synthetic; D2 overlap is label-conditioned and may invalidate labels; grayscale ≠ IR; external DMD video can be sampled as frames with careful label mapping and subject/clip grouping; missing one modality may produce mathematically correct ΔRisk>0.15; moving average lowers score noise but can delay alerts; “Fusion improves real-world high-risk detection” is not demonstrated by artificial unpaired scenario comparisons.

# E. Sign-off checklist

[ ] Real baseline model inference path exercised end-to-end.

[ ] Five-model comparison and bounded hyperparameter tuning documented without test leakage.

[ ] Vision corruption 6×3 and Telemetry D0–D3 generator + raw results exist.

[ ] E2–E5 scripts and scenario/test oracles pass methodological review.

[ ] Unit, integration, system, negative/error handling tests actually run.

[ ] Performance P95/1s and logging 99% criteria measured, not assumed.

[ ] UAT execution evidenced or clearly NOT YET DONE.

[ ] Week 7 full demo repeatable with a clean documented start.

[ ] Ch4–7 contents aligned with actual repo evidence and rubric.